## Slide 1
Climate Change Adaptation
Working Group (CCA WG)
Mr. Iki Peter
Chair of CCA WG
November 2022

## Slide 2
Outline
Focal Points
Action taken for SOM-16 Decisions
Joint Communique
Update on Workplan and Budget by the Chair of CCA WG for 2022
Workplan and proposed Budget by the Chair of CCA WG for 2023
Draft Recommendations for SOM-17

## Slide 3
Focal Points
Member Country | Focal Points
Indonesia (Co- Chair) | Focal Point: Ms. Sri Tantri Arundhati, Director for Climate Change Adaptation, Ministry of Environment and Forestry Alternate: Mr. Muhammad Yusuf, Director for Coastal and Small Islands Utilization, Ministry of Marine Affairs and Fisheries. Alternate: : Ms. Nuraeni, Ministry of Environment and Forestry
Malaysia | Focal Point: Madam Noor Afifah Abdul Razak, Deputy Secretary General (Environment), Ministry of Environment and Water Alternate: Dr Ejria Saleh, Borneo Marine Research Institute, Universiti Malaysia Sabah
Papua New Guinea (Chair) | Focal Point: Mr. Iki Peter, Acting Manager for Adaptation, Adaptation and Projects Division, Climate Change and Development Authority. Alternate: Ms. Stephenie Rere, Adaptation Officer, Adaptation and Projects Division, Climate Change and Development Authority.
Philippines | Ms. Elenida Basug, Director of DENR Climate Change Service; Alternate: John Erick Avelino, Biodiversity Management Bureau and Mr. Albert Magalang, DENR Climate Change Service
Solomon Islands | Marlchom Zion Row, Senior Climate Change Officer, Climate Change Division, Ministry of Environment, Climate Change, Disaster Management and Meteorology Alternate: Ms. Nelly Kere, Chief Programme Officer, Ministry of Environment, Climate Change, Disaster Management and Meteorology
Timor-Leste | Mr. Rui dos Reis Pires, National Director for Biodiversity, Secretary State for Environment Alternate: Mr. Junior Pascoal Carvalho, Chief of Administration Section under the national directorate of research development of Aquaculture and fisheries

## Slide 4: Action taken for SOM-16 Decisions
Decisions | Status
Acknowledged and appreciated the presentation by CCA Working Group (Annex 52); | Done
Acknowledged the draft Climate Change Communique noting that it would be further discussed in the working group (Annex 53); | Based on 27 Oct meeting and Pre-SOM 17, countries to confirm the signatory whether the Minister or Directorate General
Acknowledged the progress of the webpage for the virtual Center of Excellence (COE) and tasked the Regional Secretariat to work with CCA working group to finalize the draft webpage (link: http://vcoe.coraltriangleinitiative.org/); | Based on 27 Oct meeting, country agreed to capture the achievement through another platform e.g. CT Atlas
Agreed to hold online events in 2022 for the 7th Regional Exchange back-to-back with 7th CCA Working Group Meetings due to the COVID pandemic situation; | Postpone to 2023 (In-Person)
Acknowledged the support of the USAID/RDMA through the Sustainable Fish Asia (SUFIA) project to support the activities of the CCA Working Group; | SUFIA LCD conducted a webinar on CCA Executive Course on 28 July 2022 for the local leaders
Supported the recommendations of the CCA Working Group to handover the Chair from the Philippines to Papua New Guinea and the handover of the Co-Chair from Papua New Guinea to Indonesia; | Done
Appreciated the active contributions of Commissioner Noel Antonio V. Gaerlan as Chair from the of Philippines and Co-Chair Ms. Luanne Losi-Yawingu of Papua New Guinea for the period of 2018-2021; and | Done
Approved the CCA Working Group 2022 Workplan (Annex 54). | Done

## Slide 5: Joint Communique - Name of the Ministers
Indonesia
--------------------------------
Acting Director General
Marine and Spatial Management
Ministry of Marine Affairs and Fisheries
Malaysia
--------------------------------
Director General
Ministry of Environment and Water
Papua New Guinea
--------------------------------
Hon. Simon Kilepa, MP
Ministry of Environment, Conservation and Climate Change
Philippines
--------------------------------
Secretary
Department of Environment and Natural Resources
Solomon Islands
--------------------------------
Hon. Stanley Festus Sofu
Ministry of Environment, Climate Change, Disaster Management & Meteorology
--------------------------------
Hon. Nestor Giro
Ministry of Fisheries and Marine Resources
Timor-Leste
--------------------------------
Name of Minister
Which Ministry
Based on the discussion during the CCA In-Situ WG meeting on 27 October 2022,
ID, MY, TL: Director General Level
PG, PH, SB: Ministerial Level
TL: TBC (2-3 weeks)

## Slide 6: Update on Workplan and Budget for 2022
Planned Activities | Time Frame | Budget (USD) | Status
Back-to-back with 7th CCA Working Group Meeting Regional Exchange: Developing CEPA and Strategy for CCA (online) | Q3-Q4 | Virtual meeting USD 5,280 | CCA WG In-situ online Meeting was conducted on 27 Oct 2022 Agree to move in 2023 (In-person meeting)
Finalization of Executive Course Climate and Coastal Vulnerability and Risk Profiling (Tools and Approaches) | Q2, (SUFIA can only support until June 2022 latest) | Finalization of Executive Course will be supported by USAID-SUFIA for webinar 1 and 2. | Conducted the Climate Change Adaptation Executive Course 1 (July 2022). Course 2 was not conducted due to time constraint and other concerns Waiting for the countries review and approval on the guidebook of Vulnerability Assessment Tool produced by PH for CT6 countries to be use in the workshop (Executive Course).

## Slide 7: Workplan and Propose Budget for 2023
Planned Activities | Time Frame | Budget (USD)
7th CCA Working Group Meeting together with Regional Exchange: Developing CEPA and Strategy for CCA | Q1 or Q2 | USD 8,500
Finalization of Executive Course 2nd part of the course |  | Support from the partner
Workshop on Conducting the vulnerability assessments to achieve Target Output B3.1.1 By 2025, Exposure and vulnerability levels including projections on climate change risks are established and reported through the mid-term report in the CT Region |  | Support from the partner
Workshop to update and disseminate of CT6 climate change adaptation action plans to achieve Target Output B3.1.2 By 2025, relevant existing climate change adaptation action plans are updated, guided by current climate change projections and technology, and disseminated within the CT region. |  | Support from the partner

## Slide 8: Recommendations for SOM 17
Acknowledged and appreciated the presentation by CCA Working Group (Annex 1).
Adopt the Climate Change Communique to be presented at suitable platforms as decided by the CT6 member countries (Annex 2) and to be signed at the ministerial level.
Appreciated the inputs from Indonesia for the CCA Executive Course Framework Proposal.
Acknowledged and appreciated the conduct of the Online Training on Climate Change Adaptation Executive Course 1 on 28 July 2022 organized by the SUFIA LCD (Annex 3).
Acknowledged and appreciated the support of USAID RDMA through the Sustainable Fish Asia (SUFIA) to the activities related to CCA Working Group once the partnership concept note is approved.
Agreed on the conduct of 7th CCA Working Group Meeting together with 7th Regional Exchange to be undertaken in 2023 through In-Situ online. Provided there is external funding support, a physical meeting might be held.
Approved the CCA Working Group 2023 Workplan.