## Slide 1
TECHNICAL WORKING GROUP
Mr. Noel Antonio Gaerlan
SESSION 10.4: CLIMATE CHANGE ADAPTATION (CCA)TECHNICAL WORKING GROUP
Chair of CTI-CFF CCA WORKING GROUP

## Slide 2
Outline
Focal points and partners
Status of 2019 Workplan
Status on Decisions Endorsed by SOM 14
Proposed Workplan for 2020
Recommendation for SOM 15 Consideration

## Slide 3
1. Focal Points
Member Country | Focal Points
Indonesia | Sri Tantri Arundhati, Director for Climate Change Adaptation Ministry of Environment and Forestry Supported by: Nuraeni, Deputy Director for Ecological Climate Change Adaptation, Ministry of Environment and Forestry Fegi Nurhabni, Assistant Deputy Director for Climate Change Adaptation, Minitstry of Marine affairs and Fisheries
Malaysia | Dr Nagulendran Kangayatkarasu Deputy Secretary General Environment and Climate Change Ministry of Energy, Science, Technology, Environment and Climate Change (MESTECC) Supported by: Dr Ejria Saleh, Borneo Marine Research Institute, Universiti Malaysia Sabah
Papua New Guinea (Co-Chair) | Ms. Luanne Losi-Yawingu, Acting Manageress Adaptation, Climate Change and Development Authority Supported by: Iki Peter
Philippines (Chair) | Engr. Noel Antonio V. Gaerlan, Undersecretary, Climate Change Commission Supported by: Mr. Alexis D. Lapiz, CCC and John Erick Avelino, DENR
Solomon Islands | Tsatsa Seimarlie-Chakumai, Senior Adaptation Officer, Climate Change Division, Ministry of Environment, Climate Change, Disaster Management and Meteorology Supported by: Nelly Kere, and Agnetha Vave-Karamui, Ministry of Environment, Climate Change, Disaster Management and Meteorology
Timor-Leste | Rui dos Reis Pires, National Director for Biodiversity, Secretary State for Environment Supported by: Junior Pascoal Carvalho, Chief of Department Fisheries and Aquaculture, Ministry of Agriculture and Fisheries, Liqisa Municipality

## Slide 4
2. Partners
Role | Primary Partners
Technical Support | WWF, GIZ, TNC

## Slide 5
3. Status of 2019 Workplan
Activities | Status
Blue Carbon Capacity Building Workshop to be hosted by Indonesia subject to funding availability | (Completed ) July 2-4, 2019 Jakarta , Indonesia
CCA TWG Meeting (PH to host- tentative) Finalization of CCA Executive Course Familiarize and update M&E Indicators Update on Blue Carbon Capacity Building Workshop Update on Center of Excellence (COE) | (Completed) September 5-6 , 2019 Manila, Philippines
CT Atlas Inception Workshop taking into account input from CCA | Ongoing
Update the REAP through open participatory of CT6 countries. (Note: The Review of the RPOA will have elements of LEAP and REAP) | 

## Slide 6
4. Status on Decisions Endorsed by SOM 14
DECISIONS ENDORSED BY SOM 14 | STATUS
Note the need to reprioritize and appreciate the support provided by Development Partners to the CCAWG; | Ongoing
Reprioritize, revisit and refocus issues affecting CT6 member countries, particularly on CCA what to do in subsequent years for inclusion in the RPOA revision; | Done
Task the Climate Change Working Group to finalize the draft Executive Course of CCA - Introductory levels 1 and 2 – by urging CT6 member countries to provide comments by 30th March 2019; | Done
Agree to carry over the implementation of two activities - the capacity building on Blue Carbon and CEPA activity in 2019 subject to availability of funds and acknowledge Indonesia to host the activities; | Done
Urge the CT6 member countries to come up with their respective Blue Carbon roadmap / initiatives subject to national circumstances; | Done
Agree for virtual regional Center of Excellence (COE) hosted by the existing CTI website with inputs from respective national COEs through their respective NCCs; | New Recommendation
Support the recommendation of the CCA WG to turn over the Chair from Malaysia to Philippines and the turn-over of the Co-Chair from PH to PNG based on the provisions stipulated in the Rules of Procedure of the CCA WG; and | Done
Approve the CCA TWG Work Plan 2019. | Done

## Slide 7
5. Proposed Workplan for 2020
Planned Activities | Venue | Time Frame | Projected Budget (USD) | Source of Budget
CT Atlas Training Workshop (CCA Inputs) |  | Q1 (Jan – Mar) | TBC | CTI-CFF Regional Secretariat
Regional Exchange on: Climate and Coastal Vulnerability and Risk Profiling (Tools and Approaches) Developing CEPA and Strategy for CCA Finalization of Executive Course Back to back with 7th CCA Working Group Meeting | Tentative Venue Manila | June | 50,000 (from RS) | NCC of Philippines to Host with support from CTI-CFF Regional Secretariat and Development Partners

## Slide 8
6. Recommendation for SOM 15 Consideration
Noted the progress of the development of the draft TOR Executive Course and urge the CCA Working Group to finalize by 2020;
Acknowledged the urgency to increase the Resilience and Adaptive Capacity of Coastal and Marine Ecosystem through Coastal Vulnerability and Climate Risk Profiling including Development of Communication, Education and Public Awareness (CEPA) and Strategy for CCA;
Acknowledged the progress to develop the term of references (ToR) of Centre of Excellent (CoE) and agree to expand the ToR of COE to include other Thematic Areas;
Noted the need for a Communique on the impacts of climate change in the Coral Triangle Region
Endorsed CCA TWG Workplan for 2020.