## Slide 1
Update on the Recruitment and Selection of the new DEDPS from the Chair of the Appointment Committee

## Slide 2
Special SOM (28 May 2021) | Update
Update on the Recruitment of DEDPS 3.5 Acknowledged the updates and timeline on the recruitment process of the new Deputy Executive Director for Program Services (DEDPS) (Annex 13); | 23 August 2021: 1st meeting of the Appointment Committee (AC) on the Selection of new DEDPS Agreed Timeline on the Selection and Recruitment Process
Date | Activity
23 Aug 2021 | 1st meeting of the Appointment Committee (AC)
1 Oct 2021 | Deadline of submission application to RS
8 Oct 2021 | Submission of received applications to AC
18 Oct 2021 | RS received the shortlisted candidates from AC
21 Oct 2021 | 2nd meeting of the Appointment Committee Agenda: (1) identify top 5 candidates for interview; (2) Final dates for interview; (3) Interview Mechanics
25 Oct 2021 | Notification of 5 candidates for interview
3 Nov 2021 | Online Interview of the top 5 candidates Appointment Committee to discuss the result of the interview and identify recommended DEDPS
5 Nov 2021 | RS to communicate the result of the interview process to CSO
8 Nov 2021 | Official letter from CSO Chair to be sent to selected candidate for new DEDPS
Nov 2021 – Jan 2021 | RS to arrange work permit and other relevant work documentations

## Slide 3
Special SOM (28 May 2021) | RS Update
Update on the Recruitment of DEDPS 3.5 Acknowledged the updates and timeline on the recruitment process of the new Deputy Executive Director for Program Services (DEDPS) (Annex 13); | RS posted the announcement on CTI Website and CTI-CFF social media accounts and informed NCC about the job opportunity. Advertised the DEDPS Job Opportunity in the following newspapers (print) 1 Oct 2021: a total of 41 applications received (28 – ID; 1 - MY, 10 - PG, 1 – PH, and 1 SB)
Country | Newspaper | Date Published
Indonesia | Kompas Jakarta Post | 15 Sept 15 Sept
Malaysia | The Star New Strait Times | 15 Sept 23 Sept
Papua New Guinea | The National The Post Courier | 23 Sept 15 Sept
Philippines | Philippine Daily Inquirer Philippine Star | Coordinated with PH NCC; PH NCC coordinated with POEA and shared the info to RS
Solomon Islands | Solomon Star The Island Sun | 15 Sept 16 Sept
Timor-Leste | Timor Post Jornal Nacional Diario | 15 Sept 15 Sept

## Slide 4
Special SOM (28 May 2021) | Update
Update on the Recruitment of DEDPS 3.5 Acknowledged the updates and timeline on the recruitment process of the new Deputy Executive Director for Program Services (DEDPS) (Annex 13); | 
Appointment Committee members from Indonesia, Malaysia and Solomon Islands had submitted their shortlisted candidates for DEDPS on Oct 2021. Other members of the Committee have yet to submit their shortlisted candidates
2nd meeting of the Appointment Committee had been postponed twice ( 21 October 2021 and 17 November 2021) due to absence of quorum.
24 November 2021: Chair of the Appointment Committee wrote a letter to members of the Appointment Committee requesting preferred schedule for the 2nd meeting of the Committee. Members of the committee have yet to reply.

## Slide 5
1. Appreciated the excellent contribution of Dr. Sharifah Nora Asfiah Binti Syed Ibrahim as Deputy Executive Director of Program Services of the CTI-CFF Regional Secretariat for the term November 2017 – November 2021.
2. Acknowledged the update on the recruitment and selection of the new Deputy Executive Director for Program Services and tasked the Regional Secretariat to continue assisting the Appointment Committee that the Committee would best to meet as scheduled to complete recruitment and selection process.
Proposed Recommendations