## Slide 1
COUNTRY REPORT OF PHILIPPINES
Theresa Mundita S. Lim
Chair, MPA Working Group
Philippines

## Slide 2
Topic Outline
Country TWG Focal Point
Partners and Status of Partnership
Progress Towards NPOA
Progress of NPOA and CTI M&E Indicators
Lessons Learned
Challenges
Next Steps

## Slide 3
Country TWG Focal Points
TWG | FOCAL POINT
Seascapes | Theresa Mundita S. Lim Director, Biodiversity Management Bureau – DENR
EAFM | BFAR
MPA | Theresa Mundita S. Lim Director, Biodiversity Management Bureau - DENR
CCA | Noel Antonio V. Gaerlan Undersecretary, Climate Change Commission
Threatened Species | Theresa Mundita S. Lim Director, Biodiversity Management Bureau - DENR
M&E (cross cutting) | WWF-P

## Slide 4
Partners and Status of Partnership
Partners | Status | Projects and Programs
UNDP | On-going | MKBA
ADB RETA 7813 | On-going | CTI-SEA
GIZ | On-going | Sulu Sulawesi Seascape Project
IFAD | On-going | FishCORAL
USAID | On-going | ECOFISH, PROTECT Wildlife
UPMSI | On-going | CoRVA, MPA Support Network
CIP | On-going | Seascapes, MPAs and Networks, EAFM, CCA, Threatened Species, MKBA
US NOAA | On-going | NIPAS MPA Capacity Building Program, ARMS
UNEP-Reef World Foundation | On-going | Green Fins Code of Conduct

## Slide 5
Partners and Status of Partnership
Partners | Status | Projects and Programs
WWF-P | On-going | MKBA as Responsible Partner
ECOFISH/WorldFish Center | On-going | Coastal Fisheries and Poverty Reduction (COASTFISH)
BFAR-NFRDI | On-going | Tuna Genetics
RARE | On-going | MKBA as Responsible Partner

## Slide 6
Progress Towards NPOA
Goal 1: Priority Seascapes Designated and Effectively Managed |  |  | 
Total Actions | Completed | On-Going | Not Started
9 | 3 | 4 | 2*
Sustained the implementation of the management and initiative of Sulu Sulawesi Seascape Development of the 2nd Priority Seascape – West Philippine Sea MPA Network (under deliberation) Drafted the Strategic Plan |  |  | 
*Aligning Seascapes models with policy and legal framework *Promote and market seascape plans |  |  | 

## Slide 7
Progress Towards NPOA
Source: NPOA Costing
Goal 2: Ecosystem approach to management of fisheries and other marine resources is fully applied |  |  | 
Total Actions | Completed | On-Going | Not Started
24 | 6 | 18 | 0
Approved/passed RA 10654 – An Act to Prevent, Deter and Eliminate Illegal, Unreported and Unregulated Fishing, amending RA 8550 (The Philippine Fisheries Code of 1998) Mainstreaming of EAFM to national and regional programs EAFM training for Local Government Units and National Government Agencies Seasonal fisheries closure in selected parts of the country expanded (Batangas, Zamboanga and Northern Palawan) Capacity Building on law enforcement and Monitoring, Control, and Surveillance (MCS) on - going Research and management measures for tuna fisheries (held Tuna Congress, 2016) |  |  | 

## Slide 8
Progress Towards NPOA
Source: NPOA Costing
Goal 3: Marine Protected Areas (MPAs) established and Effectively Managed |  |  | 
Total Actions | Completed | On-Going | Not Started
8 | 0 | 8 | 0
Refiled Expanded National Integrated Protected Areas System Act at the 17th Congress (Housebill 133, Housebill 177 and Senate Bill No. 32) Capacity Building on Coral Reef and Associated Habitat Assessment; MPA Management; and Vulnerability Assessment for coastal habitats on-going Outstanding MPA and MPA Networks: selection process of nomination for Para El Mar 2017 is on-going and National PA Awards Implementation of Management Effectiveness Assessment using MEAT and METT MPA Database (regular updating encoding of data) Capacity Building through Masteral Program on coastal and marine Rehabilitation and Protection of Coastal and Marine Ecosystems through national program (CMEMP) Updating of MPA management plans and establishment of MPAs and MPA Networks (e.g., Sea Turtle MPA Network) Implementation of SSME work plan on the establishment of MPA network example on marine turtles and its habitats |  |  | 

## Slide 9
Progress Towards NPOA
Source: NPOA Costing
Goal 4: Climate Change Adaptation Measures Achieved |  |  | 
Total Actions | Completed | On-Going | Not Started
11 | 3 | 8 | 0
Establishment of Climate Change Academy by the Provincial Government of Bicol, Philippines Establishment of National Panel of Technical Experts (NPTE) by the Climate Change Commission “National Disaster Risk Reduction and Management Plan” Expansion and climate-smarting of the MPA network Community-based adaptation measures in terrestrial, coastal and marine regions Biophysical and Socio-Economic Vulnerability Assessments in selected coastal communities and national marine protected areas – continuing activity Climate-smart rice varieties Capacity Building for various sectors on CCA and disaster preparedness Grey-Green Infrastructure in partnership with LGUs and national governments to improve coastal protection in small island communities Income diversification of vulnerable coastal communities Build capacities on disaster risk reduction and climate change adaptation in small island communities Conduct Participatory Capacities and Vulnerabilities Assessments Availability of 1 billion pesos People’s Survival Fund (PSF) from National Government to finance adaptation measures at the local community level. Mobilization of financial and technical resources to support the national center of excellence |  |  | 

## Slide 10
Progress Towards NPOA
Source: NPOA Costing
Goal 5: Threatened Species Status Improving |  |  | 
Total Actions | Completed | On-Going | Not Started
8 | 2 | 5 | 1*
Information Campaign on protected Philippine Aquatic Wildlife Science-based expansion of the Tri-national Sea Turtle Corridor, Marine Research Foundation Country assessment of sharks, rays, batoids, and chimaeras – on-going (BFAR) Country assessment of napoleon wrasse – on-going (BFAR) Baseline assessment of napoleon wrasse in Tubbataha Reefs Natural Park – Tubbataha Management Office Publication and dissemination of relevant knowledge products Local government training for the proper handling of large marine mammals and marine turtles On-going review of marine turtles database On-going monitoring of sea birds in Ramsar and UNESCO Heritage Sites Elevate the conservation status of Thresher Shark, Panggolin, Nautilus to CITES Appendix_____ On-going development of action plan on invasive alien species |  |  | 
*Red list assessment of priority marine species in the Philippines |  |  | 

## Slide 11
Progress Towards NPOA
Goals | Accomplishments
Cross Cutting Activities 1. Communication Campaigns conducted | Month of the Ocean 2016 International Coastal Clean-Up CT Day Celebration (Science Camp for coastal High School students in El-Nido-Taytay and National Science Camp in Oriental Mindoro Developed AV material for sardines management
 | Completed and published Costing of the CTI National Plan of Action
2. Capacity Building | Proposed capacity building on the assessment and strengthening of the NCCC Strengthening of the coastal and marine sector of the DENR Program on recognizing Women Leaders from various sectors in environmental management

## Slide 12
Progress of NPOA and CTI M&E Indicators
Goal | Total Actions | Completed | Ongoing | Not Started
1 Seascapes | 9 | 3 | 3 | 3
2 EAFM | 24 | 6 | 18 | 0
3 MPA | 8 | 0 | 8 | 0
4 Climate Change | 11 | 2 | 9 | 0
5 Species | 8 | 2 | 5 | 1
Total | 60 | 12 | 39 | 9
Source: NPOA Costing

## Slide 13
Lessons Learned
Greater impact and appreciation on the significance of CTI-CFF can be attained if grounded at the grassroot and local government levels
Formal Inter-agency collaboration at national and local level enhances environmental law enforcement and other national policy implementation across various levels of governance
Experiences from the projects are lessons learned itself

## Slide 14
Close coordination with the NCCC is a necessity in the planning, implementation and reporting of the projects/programs on CTI-CFF
The NCCC acknowledges the need to be responsive to emaerging challenges and changing conditions through expanding partnerships and networking
Lessons Learned

## Slide 15
Challenges
On-going adjustments with the new administrations new national policies and priorities
Institutionalization of the goals and actions of the CTI-NPOA to the local government plans
Vulnerability of the country to natural and anthropogenic hazards/disturbances
Integration among goals of the RPOA should be strengthen

## Slide 16
Next Steps
Pilot various modalities for sustainable finance and ensure policy support for sustainable financing
Review of the National Plan of Action and the NCCC
Finalize the M&E indicators for the NPOA
Ensure the alignment of the goals and actions of the NPOA to both National and local government plans