## Sheet1
1.2 LEARNING EXCHANGE FOR CT6 COUNTRIES IN USAID OCEANS PRIORITY AREA (GENERAL SANTOS AND BITUNG)
No | Activity | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April
|  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
1 | Consultation and Coordination with OCEAN (e.g. set the date and venue) | bar: November W1; December W1
2 | Consultation and Coordination with OCEAN (e.g. formulate substantive materials such as Budget allocation, TOR, Agenda, Concept note, Invitation,identifying participants etc) | bar: November W2 to November W3
3 | Seek confirmation fromResource Persons (USDOI, USAID/RDMA, NOAA, The Oceans and Fisheries Partnerships, and SEAFDEC) | bar: November W4
4 | Coordination with local government and NCC Indonesia | bar: November W4
5 | Survey the venue and accomodation | bar: December W1
6 | Finalization Learning Exchange materials and logistics | bar: December W2
7 | Circulation of invitation letter along with substantive materials | bar: December W3
8 | Follow up on confirmation of Resource Persons and Participants | bar: December W4 to March W2
9 | Logictic preparations (e.g flight and hotel reservation, local transportation, meeting package) | bar: January W1 to February W4
10 | Media and Publication (e.g. Seminar kit, press release, backdrop, etc) | bar: February W1 to February W4
11 | Cross check preparation (internal meetings, printing materials, venue, meeting package, etc) | bar: February W1 to February W4
12 | Consultation and Coordination with OCEAN (e.g. finalization of preparation) | bar: February W1
13 | Event rehearsal | bar: March W3
14 | Event | bar: March W4
15 | Reporting | bar: April W1
16 | Consultation with OCEANs on final report | bar: April W2
17 | Coordination with TWG Chair EAFM | bar: April W3
18 | Circulation of final report | bar: April W4